## Slide 1: Project Development (IV_SYP_PRE)
Unit 10
Effort Estimation

## Slide 2: Effort Estimation vs. Scheduling

## Slide 3: Effort vs. Scheduling – A Very Rough Sketch (1)
Pre-work: Define a tasks to be done and one or more criteria per task to be satisfied in order to clearly indicate that the task is finished
Effort
  Ask one or more experts: “How much time would one single person need to accomplish this task?”
  Align these estimations to get a single and plausible number
  Alternatively ask: “How much time took this (or a similar) task in another project we did in our company (multiply by the number of people working in parallel on this task)
Do this for all of your tasks in your project

## Slide 4: Effort vs. Scheduling – A Very Rough Sketch (2)
Time
  Define a start time for your project
  Analyze the dependencies between your tasks
  Analyze the availability of resources (team members, machines, etc.) in your project
  Arrange your tasks according to the dependencies and resources

## Slide 5: A Graphical Example
A
30
B
25
C
10
D
5
E
17
F
42
G
21
H
33
Duration: 183 hours
A
30
B
25
C
10
D
5
E
17
F
42
G
21
H
33
Total effort: 188 person hours
Total effort: 188 person hours
Total effort: 188 person hours
Total effort: 188 person hours
Total effort: 188 person hours
Total effort: 188 person hours
Total effort: 188 person hours
Total effort: 183 person hours

## Slide 6: A Graphical Example
A
30
B
25
C
10
D
5
E
17
F
42
G
21
H
33
Duration: 183 hours
A
30
B
25
C
10
D
5
E
17
F
42
G
21
H
33
Duration: 143 hours

## Slide 7: Effort Estimation in Little

## Slide 8: A Simple Planning and Monitoring Sheet (PM-Sheet)
Task | Orig. Est. | Curr. Est. | Effort | Remain | Responsible

## Slide 9: A Small Exercise to Start With
  Sit down in your team
  Agree on the most important things to be accomplished in your project (tasks) in the next week
  Make sure that every team member understands every task
  Agree on one or more criteria per task which have to be fulfilled in order to indicate whether this task is finished (acceptance criteria)
  Prioritize the tasks roughly
  Document the tasks, their acceptance criteria and prios

## Slide 10: A Small Exercise to Start With – cont’d
Find out, how many person hours your team can spend on your project during the next week (hours pool)
Estimate the effort (in person hours) to accomplish these tasks
  Start your estimations with the highest prio tasks and go along the way down following the falling prios
Stop the effort estimation as soon as your estimations reach the hours pool
Document the effort estimations and your hours pool in the PM-Sheet

## Slide 11: During the Week
Every team member
  When you take over a task out of the PM-sheet write your name as responsible to this task
  Monitor your working time on the project in the PM-sheet
  Re-estimate the remaining time necessary to accomplish the task you are currently working on
Project lead
  If a new tasks comes up or a tasks becomes obsolete, update the PM-sheet

## Slide 12: A Small Exercise to Start With – One Week Later
Check, whether your planned tasks are finished by testing the actual results against the acceptance criteria
Compare these results with the remaining time as monitored in your planning sheet
Analyze the entries for every planned task
  Does the original estimation differ from the current estimation?
  If so: why did it grow or shrink?

## Slide 13: A Small Exercise to Start With – Retrospective
What did you learn for a next iteration?
What went good? Why?
What went bad? Why?
Which things have to happen again in the next iteration?
Which things must not happen again in the next iteration?

## Slide 14: Structuring the Whole Project

## Slide 15: A Bigger Picture
So far we only estimated small entities
If we estimate a complete project on this basis, we would never end
Try a slightly different approach

## Slide 16: There Is Nothing Without Requirements
Collect the requirements in a product backlog
Basis should be the requirements documented in the system spec
ID | Prio | Epic | User Story | COS (Criteria of Satisfaction) | Effort
CAL01 | 1 | Calendar | As a student I want to add an internal event | Invalid values: start after end, empty title, notification e-mail to be sent to all class mates | 3
CAL02 | 2 | Calendar | As a student I want to cancel an internal event | Notification mail to all class mates | 1
CAL03 | 2 | Calendar | As a teacher I want to add an internal event | Only classes which are assigned to teacher may be selected; all acceptance criteria from CAL01 have to be fulfilled | 5
… | … | … | … | … | …
… | … | … | … | … | …

## Slide 17: User Story
One to two sentences
Criteria of satisfaction
INVEST
  Independent
  Negotiable
  Valuable
  Estimable
  Small
  Testable

## Slide 18: User Stories have Different Levels of Detail
User stories with high priority have a high level of detail
User stories with low priority have a low level of detail
Over time user stories evolve and get a higher level of detail
Calendar
As a student I want to add an event
As a student I want to select the classes which are to be invited
As a student I want to get suggestions when the invited classes have a common time slot.
At the very beginning its maybe only the Epic

## Slide 19: An Even Bigger Picture
It is difficult to describe a complete project even on this level of detail
The next three sprints are maybe fine with this approach but then?
Let’s start off with something rougher
  Work breakdown structure
  Story map

## Slide 20: Work Breakdown Structure
Solar Mobil
Engineering
Production
Mounting
R & D
Collector
E-Engine
Chassis
Board Electr.
Analysis
Design
Implement.
Test
Function oriented
Object oriented
Time oriented

## Slide 21: Story Maps
Calendar | Forum | FTP | Epic | Epic … | Epic
CAL01 | FOR01 | FTP01 | STORY | STORY | STORY
CAL02 | FOR02 | FTP02 | STORY | STORY | STORY
CAL03 | FOR03 | FTP03 | STORY | STORY | STORY
CAL04 | FOR04 | FTP04 | STORY | STORY | STORY
CAL05 |  | FTP05 | STORY |  | STORY
… |  | … |  |  | …
Time

## Slide 22: Effort Estimation for the Whole Project

## Slide 23: Effort Estimation of the Bigger Entities
The bigger entities can’t be estimated in hours
Estimation in days or story points

## Slide 24: Story Points
No effort
Very small effort
Small effort: approx. double of a very small effort

## Slide 25: Story Points – continued
Middle effort: Very small + small effort
Large effort: Small + middle effort
Very large effort: Middle + large effort

## Slide 26: Story Points – finished
Huge effort: Large + very large effort

## Slide 27: Distance of Story Points
0, 1, 2, 3, 5, 8, 13
The Fibonacci Sequence
Increasing distances
  Reliefs the team from guessing around whether a specific story has an effort of 21 or 25 hours
  ATTENTION: If effort is 13 for a high number of stories, the team most probably doesn’t understand a large part of the project

## Slide 28: Story Points – Characteristics
Team specific
  Different teams will estimate a different amount of points
Relative
  One estimation has no meaning

## Slide 29: Effort Estimation w/ Story Points – The Planning Poker
Prerequisite: Every team member has a stack of cards (one from each kind)
Select a small story at first
Product Owner explains story
Team clarifies story (ask and discuss)
Every team member selects a card from his / her stack reflecting his opinion concerning the effort
All team members unhide their cards at the same time

## Slide 30: The Planning Poker – continued
If all team members estimate the same effort, we are done
If not
  The member with the smallest estimate explains his/her reasons
  The member with the highest estimate explains his/her reasons
Then a new round of estimation starts

## Slide 31: Putting it all Together

## Slide 32
copyright: www.goodagile.com

## Slide 33
copyright: www.goodagile.com
Product Owner:
has a vision of a product

## Slide 34
copyright: www.goodagile.com
Product Backlog:
Holds all features and requirements

## Slide 35
copyright: www.goodagile.com
Sprint:
Typical duration (2 - 6 weeks)
Within these features are implemented

## Slide 36
copyright: www.goodagile.com
Sprint Planning Meeting:
Product owner and team together
Features in Product Backlog are prioritized
Sprint Backlog is created
Detailed plan of work is done

## Slide 37
copyright: www.goodagile.com
No Changes:
Planned features for a sprint must not be changed

## Slide 38
copyright: www.goodagile.com
Daily Scrum Meeting:
Daily meeting to exchange progress, next step, impediments (problems)
Progress update in Burndown Chart

## Slide 39
copyright: www.goodagile.com
Scrum Master:
Handles organizational issues
Resolves impediments

## Slide 40
copyright: www.goodagile.com
Product:
Every sprint results in „shipable“ software

## Slide 41
copyright: www.goodagile.com
Sprint Review:
Results of sprint are reviewed
Stakeholders sign off the implemented features

## Slide 42
copyright: www.goodagile.com
Sprint Retrospective:
Internal review of work in last sprint
List of Oks and NGs
Continuous improvement of work

## Slide 43: Traditional Methods
Formal estimation models
  Function Points
Expert estimations
  Group estimation, Work breakdown structure based models
Combination-based estimations
  Mechanical combination

## Slide 44: Function Points

## Slide 45: Group Estimation

## Slide 46: WBS-Based Estimation

## Slide 47: Mechanical Combination
Average of function points and WBS-based estimations